## Jira_Backlog
Issue ID | Issue Type | Title | Description | Priority | Story Points | Assigned To | Branch Name | Status
TR-0 | Task | Create Documentation | Create SRS , Jira Task Sheet, Presentation, Final Report | High | 4 | Manoj | document-setup | Done
TR-1 | Task | Project Setup | Initial project setup with Flask structure and GitHub repo | High | 8 | Manoj | feature/project-setup | Done
TR-2 | Task | Setup Flask App | Create basic Flask app structure and routes | High | 5 | Manoj | feature/flask-setup | To Do
TR-3 | Task | Integrate NLP Model | Load helsinki-NLP/opus-mt-en-hi model using transformers | High | 13 | Manoj | feature/model-integration | To Do
TR-4 | Task | Create Translation API | Create POST API endpoint for translation | High | 8 | Manoj | feature/translation-api | To Do
TR-5 | Task | Frontend UI Design | Design HTML and CSS UI for translator | Medium | 5 | Prajapati | feature/ui-design | To Do
TR-6 | Task | Input Validation | Validate empty input and handle errors | Medium | 3 | Manoj | feature/input-validation | To Do
TR-7 | Task | Error Handling | Implement try-except and user-friendly error messages | Medium | 3 | Manoj | feature/error-handling | To Do
TR-8 | Task | Deploy on Render | Deploy Flask app on Render cloud platform | High | 8 | Manoj | feature/render-deployment | To Do
TR-9 | Task | Create requirements.txt | Add required dependencies for deployment | Low | 2 | Manoj | chore/requirements-file | To Do
TR-10 | Task | Testing & Bug Fixing | Perform unit testing and fix bugs | Medium | 5 | Manoj | feature/testing | To Do